## Sheet1
Project Name |  | Klik Moris Site Dashboard | Environment
Tester's Name |  | Tanvir Hasan | Reviewed By
Date Tested |  | 31-05-2023 | Version | 1
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment | Dev Name | Dev Status | QA Status
1 | Hotel List | Add New Hotel | New hotel added on Frontend but not showing at backend | 1. Go to Dashboard 2. Click Hotel List 3. Add new Hotel | Bug | High | High |  |  |  | Shykot | Done | Fixed
2 | Hotel List | Delete Existing Hotel | Delete existing hotel from the list not working | 1. Go to Dashboard 2. Click Hotel List 3. Delete Existing Hotel List | Bug | High | High |  |  |  | Shykot | Done | Yet Have Some problem. Frontend contains some hotel names those are not available on backends
3 | Hotel List | Update Existing Hotel | Update existing hotel from the list not working | 1. Go to Dashboard 2. Click Hotel List 3. Update Existing Hotel List | Bug | High | High |  |  |  | Arup | Done | Update is possible but Yet Have Some problem. Frontend contains some hotel names those are not available on backends
4 | Dashboard | Profile & Settings | Dashboard profile and settings on click function is not working | 1. Go to Dashboard 2. Click on profile/settings | Bug | High | High |  |  | https://prnt.sc/gL4ci4RnoE4U
5 | Hotel List | Invalid Contact | Invalid contact number accepted | 1. Go to Dashboard 2. Click Hotel List 3. Add new Hotel | Bug | Medium | High |  |  | https://prnt.sc/6s4eXIVCzXA9 | Shykot | Done | Issue: https://www.awesomescreenshot.com/video/17919858?key=709c2405a07564822f1bae10a791d767
6 | Hotel List | Add New Hotel | Hotel list can added without images | 1. Go to Dashboard 2. Click Hotel List 3. Add new Hotel | Bug | High | High |  |  |  | Neamot | done | Not Fixed Yet
7 | Facility List | Add room facility | Room facilty not showing on the list | 1. Go to Dashboard 2. Click Hotel Config 3.Click on facility List 4. Add room facility | Bug | High | High |  |  |  | Neamot | done | Not Fixed Yet
8 | Country List | Add New Country | Non numeric country code accepted | 1. Go to Dashboard 2. Country List 3. Add new country | Bug | Medium | Medium | [5 empty] | Fixed | country code can have + character
9 | Driver | Add New Driver | New driver is not added successfully | 1. Go to Dashboard 2. Click Driver 3. Add new Driver | Bug | High | High |  |  | https://prnt.sc/1gnk1vYKmHgE | Neamot | done | Fixed | run migration for driver table
10 | Driver | Edit Driver | driver is not able to edit maybe some code error | 1. Go to Dashboard 2. Click Driver 3. Edit Driver | Bug | High | High |  |  | https://prnt.sc/mawb3anQaVEC | Neamot | done | Fixed | run migration for driver table
11 | Vendor | Add/Update Vendor | Non numeric phone number accepted | 1. Go to Dashboard 2.Go to Vendor 3.Update Vendor | Bug | Medium | Medium |  |  | https://prnt.sc/RVbpZoC3UtFg | Neamot | done | Fixed | phone number can have special character.like +1 (764) 564-2035
12 | Transport | Assign Driver | driver is not able to edit maybe some code error | 1. Go to Dashboard 2. Click Transport> Assign Driver list 3. Edit Driver | Bug | High | High |  |  | https://prnt.sc/mawb3anQaVEC | Neamot | done | Fixed | run migration for driver table
13 | Transport | Transport Booking | Can not add phone number while I select a customer | 1. Go to Dashboard 2. Click Transport> Transport booking 3.Add new transport Booking | Bug | Medium | Medium |  |  | https://prnt.sc/70tqJRKTzKTf | Neamot | done | Fixed
14 | Tour ERP | Tour Booking | on tour booking no activity option to select & addressbar input system is not working | 1. Go to Dashboard 2. Click Tour ERP> Tour booking 3.Add new tour booking | Bug | High | High |  |  | https://prnt.sc/1ip937EUZyoy | Neamot
15 | Tour ERP | Tour Packages | handle exception error when I click Tour Packages | 1. Go to Dashboard 2. Click Tour ERP> Tour Packages | Bug | High | High |  |  | https://prnt.sc/lbAUCR5oOL5Q